## ProductBacklog
PRODUCT BACKLOG
Batch 2018_2019
SPRINT BACKLOG | US ID | BACKLOG ITEM |  |  | PRIORITY | RESPONSIBLE | ESTIMATE DATE | REMARKS
|  | AS A/AN | I WANT TO | SO THAT
1 | SB1/US1 | Super Admin | Provide Login ID For Schools/Colleges | The Students of That College/School can login | 1
2 | SB1/US2 | Student/Alumni | Student/Alumni Enter their Profiles | Each can view/Edit Their Profile | 1
3 | SB1/US3 | Student/Alumni | Student/Alumni Enter their Name | Other Student/Alumni Can See The Their Name | 1
4 | SB1/US4 | Student/Alumni | Student/Alumni Enter Their City | Other Student/Alumni Can See The Their City | 1
5 | SB1/US5 | Student/Alumni | Student/Alumni Click on Save Button | they can save their profile. | 1
6 | SB1/US6 | Student/Alumni | Student/Alumni Enter Their work Stream | Other Student/Alumni can see their woking Stream | 1
7 | SB1/US7 | Student/Alumni | Create The Group | They Create The Student-Alumni Connection Group | 1
8 | SB1/US8 | Student/Alumni | Join The Group | They Join a Group with using Joining Request | 1
9 | SB1/US9 | Student/Alumni | Connect Through Chat | They can Chat and Get connect With Each Other, by Creating Groups | 2
10 | SB1/US10 | Student/Alumni | Data Sharing | They Can Sends data as Files , Documents etc. | 2
11 | SB1/US11 | Student/Alumni | Image Sharing | They can Sends Image Fie within the Group | 2
12 | SB1/US12 | Student/Alumni | Viewing Profiles | They can view other Group Members profiles and Working era | 2
13 | SB1/US13 | Student/Alumni | Create Blog Feature | They can Share their Views or Experience as Blogs in a Common platform | 2
14 | SB1/US14 | Student/Alumni | Click On EditText in Blog Feature | They can Write Their blogs. | 2
15 | SB1/US15 | Student/Alumni | Click on Post button | They can Post their Blogs. | 2
16 | SB1/US16 | Student/Alumni | Create Events Feature | They can Create Events and its details on this panel and share the Information | 2
17 | SB1/US17 | Student/Alumni | Click On EditText in Event Feature | They can Write The details of Events. | 2
18 | SB1/US18 | Student/Alumni | Click on Post button | They can Post the Created Event. | 2
19 | SB1/US19 | Group Admin | Remove the group member | Group Admin have authority to remove any of group member for any wrong behaviour | 2
20 | SB1/US20 | Student/Alumni | Left the group | I do not want to receive any other information further | 2
21 | SB1/US21 | Student/Alumni | Student/Alumni Post The Event In Event Feature | Event Show To Every One | 3
22 | SB1/US22 | Student/Alumni | Student/Alumni Post The Blog In Blog Feature | Blog Show To Every One | 3
23 | SB1/US23 | Student/Alumni | They Click On Blog Button Feature | They Can See All The Blogs | 3
24 | SB1/US24 | Student/Alumni | They Click On Event Button Feature | They Can See All The Events Happened Datewise | 3
25 | SB1/US25 | Student/Alumni | Download The Image | They Can See The Image after download | 3
26 | SB1/US26 | Student/Alumni | View The Message | They Can See The Message | 3
27 | SB1/US27 | Student/Alumni | View The Events | They Can See The Event | 3
28 | SB1/US28 | Student/Alumni | View The Blog | They Can Read My Blog | 3
29 | SB1/US29 | Student/Alumni | Change The Blog Language | They Can post the Blogs in both languages (Hindi/English) | 3
30 | SB1/US30 | Student/Alumni | Student/Alumni Logout That Page | They Come At Login Page | 3
31 | SB1/US31 | DBA | Add Firebase Library | I Can Use The Services Of The Firebase | 1
32 | SB1/US32 | DBA | Add Firebase Authentication Library | I Can Use The Services Of The Firebase Authentication | 1
33 | SB1/US33 | DBA | Provide The UUID To All User | I Can Uniquely Identify The User | 1
34 | SB1/US34 | DBA | Set The Data In Tree Structure | I Can Read The Data Easely | 1
35 | SB1/US35 | DBA | Make The Reference All Data | I Can Identyfy The Data | 1
36 | SB1/US36 | DBA | Provide Unique Key To All The Data | I Can Retrive The Data | 1
37 | SB1/US37 | DBA | Private the Rules in Database | only Authorized users can View & Modify the databse | 1
38 | SB1/US38 | Admin(Director) | Provide Login ID for Students | Students can Login in the Application and Enter their Details | 1
39 | SB1/US39 | Admin(Director) | Allotcate The Login ID For Alumni | Alumni can Login in the Application and Enter their Details | 1
40 | SB1/US40 | Admin(Director) | View The Blogs/Events | They Can Monitor The Current Blogs/Event | 2
41 | SB1/US41 | Admin(Director) | Modify The Blogs/Events | They Can Remove The Wrong Events And Abuse Blogs | 2
42 | SB1/US42 | Admin(Director) | View The Profile Of Students | They Can see the details of the Students | 1
43 | SB1/US43 | Admin(Director) | View The Profile Of Alumni | They Can See the details Profiles of the Alumni | 1
44 | SB1/US44 | Admin(Director) | Remove the group member | They Can Maintain The Discipline In The Group | 3
45 | SB1/US45 | Admin(Director) | Remove/Change the Group Admin | They can Change or Remove the Group Admin | 3

## SprintBacklog 1
SPRINT BACKLOG 1
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 1 - <AlmaMates>
SB1/US1 | SuperAdmin provide login for School/College | SB1/D1/T1 | User Interface For login |  | COMPLETED
|  | SB1/D1/T2 | Validations for login details |  | COMPLETED
|  | SB1/D1/T3 | Connect login page with Firebase |  | COMPLETED
|  | SB1/D1/T4 | Fetch the data |  | COMPLETED
|  | SB1/D1/T5 | Match the data From the server |  | COMPLETED
|  | SB1/D1/T6 | login User , if Credential matched |  | COMPLETED
SB1/US2 | Sign Up Into Application | SB1/D2/T1 | User Interface For Sign Up |  | COMPLETED
|  | SB1/D2/T2 | Validations for Sign Up details |  | COMPLETED
|  | SB1/D2/T3 | Connect Sign Up page with Firebase |  | COMPLETED
|  | SB1/D2/T4 | Add The Data To Server |  | COMPLETED
|  | SB1/D2/T5 | Sign Up User |  | COMPLETED
SB1/US3 | Profile Details of Alumni/Students | SB1/D3/T1 | User Interface For Profile Register |  | COMPLETED
|  | SB1/D3/T2 | Validations for Profile details |  | COMPLETED
|  | SB1/D3/T3 | Connect with the database |  | COMPLETED
|  | SB1/D3/T4 | save the data and upload to the Firebase(Databse) |  | COMPLETED
SB1/US4 | Create/Join the Group | SB1/D4/T1 | User Interface for Create and Join The Group |  | COMPLETED
|  | SB1/D4/T2 | Validations for Group Details |  | COMPLETED
|  | SB1/D4/T3 | Coonnect with the database and save the details |  | COMPLETED
|  | SB1/D4/T4 | Send Group Joining Request from user to server |  | COMPLETED
|  | SB1/D4/T5 | Joining request from server to the Group admin |  | COMPLETED
SB1/US5 |  | SB1/D5/T1
SB1/D5/T2
SB1/D5/T3
SB1/D5/T4
SB1/US27 |  | SB1/D6/T1
SB1/D6/T2
SB1/D6/T3
SB1/D6/T4
SB1/D6/T5
SB1/US27 |  | SB1/D7/T2
SB1/D7/T3
SB1/D7/T4
SB1/D7/T5
SB1/US150 |  | SB1/D8/T1
SB1/D8/T2
SB1/D8/T3
SB1/D8/T4
SB1/US28 |  | SB1/D9/T1
SB1/D9/T2
SB1/D9/T3
SB1/D9/T4
SB1/D9/T5
SB1/US50 |  | SB1/D10/T1
SB1/D10/T2
SB1/D10/T3
SB1/D10/T4
SB1/D10/T5
SB1/US53 |  | SB1/D11/T2
SB1/D11/T3
SB1/D11/T4
SB1/D11/T5
SB1/US55 |  | SB1/D12/T1
SB1/D12/T2
SB1/D12/T3
SB1/D12/T4
SB1/US51 |  | SB1/D13/T1
SB1/D13/T2
SB1/D13/T3
SB1/D13/T4
SB1/D13/T5
SB1/US70 |  | SB1/D14/T1
SB1/D14/T2
SB1/D14/T3
SB1/D14/T4
SB1/D14/T5
SB1/US71 |  | SB1/D15/T2
SB1/D15/T3
SB1/D15/T4
SB1/D15/T5
SB1/US72 |  | SB1/D16/T1
SB1/D16/T2
SB1/D16/T3
SB1/D16/T4

## SB Hours 01
Sprint Backlog 1
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
1 | As a developer I want to login into Page | Search the Login Page |  | Completed
|  | Need Email Id |  | Completed
|  | Need Password |  | Completed
|  | Search the Login Button |  | Completed
2 | As a developer I want to search for applications to be developed so that I can Sign Up in Application | Search of Sign Up page |  | Completed
|  | Known the Username |  | Completed
|  | Known the Password |  | Completed
|  | search the Sign Up button |  | Completed
3 | As a developer I want to Create a Profile | Start with Enter the Name |  | Completed
|  | Enter the another detail |  | Completed
Search For Sign Up button
Click on sign up button
4
5
6
7
8
9
10

## SB BD Ch01
Spring Backlog 01 burn down chart
Date | Planned Total Task | Actual Incompleted Task
2018-09-04 | 3 | 0 | Tasks
2018-09-12 | 3 | 0
2018-09-11 | 3 | 0
2018-09-14 | 3 | 0
2018-09-16 | 3 | 0
2018-09-18 | 4 | 0
Days

## SprintBacklog 2
SPRINT BACKLOG 2
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 2 - <AlmaMates>
SB2/US1 | Featch the Contact | SB2/D1/T1 | Designing the Modal Class
|  | SB2/D1/T2 | Connection with database
|  | SB2/D1/T3 | Fetch the data from the database
|  | SB2/D1/T4 | Fetch the data from the contact list
|  | SB2/D1/T5 | Match the data from database and contact list
SB2/US2 | Add Chat feature | SB2/D2/T1 | Designing of GUI
|  | SB2/D2/T2 | user1 write the message and send meassage
|  | SB2/D2/T3 | message go to the Server
|  | SB2/D2/T4 | user2 featch the message from the user1
|  | SB2/D2/T5 | user1 Send the image
|  | SB2/D2/T6 | image go to the Server
|  | SB2/D2/T7 | user2 featch the image from the user1

## SB Hours 02
Sprint Backlog 2
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
1 | As a developer I want to featch the contact | Search for contact from contact list |  | Completed
|  | featch the data from databse |  | Completed
|  | compare the contact list |  | Completed
|  | show the contact list |  | Completed
2 | As a developer I want to add the feature of chat | write the meassage |  | Completed
|  | send the meassage |  | Completed
|  | retrive the meassage |  | Completed

## SB BD Ch02
Spring Backlog 02 burn down chart
Date | Planned Total Task | Actual Uncompleted Task
2017-09-25 | 2 | 0 | Tasks
2017-09-28 | 2 | 0
2017-10-02 | 2 | 0
2017-10-05 | 2 | 0
2017-10-07 | 2 | 0
2017-10-09 | 4 | 0
0
Days

## SprintBacklog 3
SPRINT BACKLOG 3
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 3 - <AlmaMates>
SB3/US1 | Add Blog Feature | SB2/D3/T1 | Designing of GUI
|  | SB2/D3/T2 | Add the Blogger Name
|  | SB2/D3/T3 | Connection with database to update the status in the database.
|  | SB2/D3/T4 | Write the Blog
|  | SB2/D3/T5 | poast inside the blog
|  | SB2/D3/T6 | update the status in the database.
|  | SB2/D3/T7 | featch the blog from database
|  | SB2/D3/T8 | user can see the blog
|  | SB2/D3/T9 | add the Event
|  | SB2/D3/T10 | update the status in the database.
|  | SB2/D3/T11 | featch the event from database
|  | SB2/D3/T12 | user can see the event

## SB Hours 03
Sprint Backlog 3
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
| As a developer I want to add blog feature | Search for write the blog
Enter the blog
Read thr blog
Verified By:
(Product Owner)

## SB BD Ch03
Spring backlog 3 Burnt Down chart
Date | Planned Total Task | Actual Uncompleted Task
2018-10-16 | 2 | 2 | Tasks
2018-10-18 | 2 | 2
2018-10-20 | 2 | 2
2018-10-21 | 2 | 2
2018-10-22 | 2 | 2
2018-10-23 | 2 | 2
0
Days

## SprintBacklog 4
SPRINT BACKLOG 4
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 4 - <Digital College>

## SB Hours 04
Sprint Backlog 4
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch04
Date | Planned Total Task | Actual Uncompleted Task
2019-01-10 | 190 | 190 | Tasks
2019-01-11 | 110 | 190
2019-01-12 | 80 | 190
2019-01-13 | 25 | 190
2019-01-14 | 15 | 190
2019-01-15 | 0 | 190
0
Days