## ProductBacklog
PRODUCT BACKLOG
Batch 2018_2019
SPRINT BACKLOG | US ID | BACKLOG ITEM |  |  | PRIORITY | RESPONSIBLE | ESTIMATE DATE | REMARKS
|  | AS A/AN | I WANT TO | SO THAT
1 | SB1/US1 | Super Admin | Provide Login ID For Schools/Colleges | The Students of That College/School can login | 1
2 | SB1/US2 | Student/Alumni | Student/Alumni Enter their Profiles | Each can view/Edit Their Profile | 1
3 | SB1/US3 | Student/Alumni | Student/Alumni Enter their Name | Other Student/Alumni Can See The Their Name | 1
4 | SB1/US4 | Student/Alumni | Student/Alumni Enter Their City | Other Student/Alumni Can See The Their City | 1
5 | SB1/US5 | Student/Alumni | Student/Alumni Click on Save Button | they can save their profile. | 1
6 | SB1/US6 | Student/Alumni | Student/Alumni Enter Their work Stream | Other Student/Alumni can see their woking Stream | 1
7 | SB1/US7 | Student/Alumni | Create The Group | They Create The Student-Alumni Connection Group | 1
8 | SB1/US8 | Student/Alumni | Join The Group | They Join a Group with using Joining Request | 1
9 | SB1/US9 | Student/Alumni | Connect Through Chat | They can Chat and Get connect With Each Other, by Creating Groups | 2
10 | SB1/US10 | Student/Alumni | Data Sharing | They Can Sends data as Files , Documents etc. | 2
11 | SB1/US11 | Student/Alumni | Image Sharing | They can Sends Image Fie within the Group | 2
12 | SB1/US12 | Student/Alumni | Viewing Profiles | They can view other Group Members profiles and Working era | 2
13 | SB1/US13 | Student/Alumni | Create Blog Feature | They can Share their Views or Experience as Blogs in a Common platform | 2
14 | SB1/US14 | Student/Alumni | Click On EditText in Blog Feature | They can Write Their blogs. | 2
15 | SB1/US15 | Student/Alumni | Click on Post button | They can Post their Blogs. | 2
16 | SB1/US16 | Student/Alumni | Create Events Feature | They can Create Events and its details on this panel and share the Information | 2
17 | SB1/US17 | Student/Alumni | Click On EditText in Event Feature | They can Write The details of Events. | 2
18 | SB1/US18 | Student/Alumni | Click on Post button | They can Post the Created Event. | 2
19 | SB1/US19 | Group Admin | Remove the group member | Group Admin have authority to remove any of group member for any wrong behaviour | 3
20 | SB1/US20 | Student/Alumni | Left the group | I do not want to receive any other information further | 3
21 | SB1/US21 | Student/Alumni | Student/Alumni Post The Event In Event Feature | Event Show To Every One | 2
22 | SB1/US22 | Student/Alumni | Student/Alumni Post The Blog In Blog Feature | Blog Show To Every One | 2
23 | SB1/US23 | Student/Alumni | They Click On Blog Button Feature | They Can See All The Blogs | 2
24 | SB1/US24 | Student/Alumni | They Click On Event Button Feature | They Can See All The Events Happened Datewise | 2
25 | SB1/US25 | Student/Alumni | Download The Image | They Can See The Image after download | 3
26 | SB1/US26 | Student/Alumni | View The Message | They Can See The Message | 2
27 | SB1/US27 | Student/Alumni | View The Events | They Can See The Event | 2
28 | SB1/US28 | Student/Alumni | View The Blog | They Can Read My Blog | 2
29 | SB1/US29 | Student/Alumni | Change The Blog Language | They Can post the Blogs in both languages (Hindi/English) | 2
30 | SB1/US30 | Student/Alumni | Student/Alumni Logout That Page | They Come At Login Page | 3
31 | SB1/US31 | DBA | Add Firebase Library | I Can Use The Services Of The Firebase | 1
32 | SB1/US32 | DBA | Add Firebase Authentication Library | I Can Use The Services Of The Firebase Authentication | 1
33 | SB1/US33 | DBA | Provide The UUID To All User | I Can Uniquely Identify The User | 1
34 | SB1/US34 | DBA | Set The Data In Tree Structure | I Can Read The Data Easely | 1
35 | SB1/US35 | DBA | Make The Reference All Data | I Can Identyfy The Data | 1
36 | SB1/US36 | DBA | Provide Unique Key To All The Data | I Can Retrive The Data | 1
37 | SB1/US37 | DBA | Private the Rules in Database | only Authorized users can View & Modify the databse | 1
38 | SB1/US38 | Admin(Director) | Provide Login ID for Students | Students can Login in the Application and Enter their Details | 1
39 | SB1/US39 | Admin(Director) | Allotcate The Login ID For Alumni | Alumni can Login in the Application and Enter their Details | 1
40 | SB1/US40 | Admin(Director) | View The Blogs/Events | They Can Monitor The Current Blogs/Event | 2
41 | SB1/US41 | Admin(Director) | Modify The Blogs/Events | They Can Remove The Wrong Events And Abuse Blogs | 2
42 | SB1/US42 | Admin(Director) | View The Profile Of Students | They Can see the details of the Students | 1
43 | SB1/US43 | Admin(Director) | View The Profile Of Alumni | They Can See the details Profiles of the Alumni | 1
44 | SB1/US44 | Admin(Director) | Remove the group member | They Can Maintain The Discipline In The Group | 3
45 | SB1/US45 | Admin(Director) | Remove/Change the Group Admin | They can Change or Remove the Group Admin | 3

## SprintBacklog 1
SPRINT BACKLOG 1
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 1 - <AlmaMates>
SB1/US1 | SuperAdmin provide login for School/College | SB1/D1/T1 | User Interface For login
|  | SB1/D1/T2 | Validations for login details
|  | SB1/D1/T3 | Connect login page with Firebase
|  | SB1/D1/T4 | Fetch the data
|  | SB1/D1/T5 | Match the data From the server
|  | SB1/D1/T6 | login User , if Credential matched
SB1/US2 | Login Into Application | SB1/D2/T1 | User Interface For login
|  | SB1/D2/T2 | Validations for login details
|  | SB1/D2/T3 | Connect login page with Firebase
|  | SB1/D2/T4 | Fetch and Match Data
|  | SB1/D2/T5 | login User , if Credential matched
SB1/US3 | Profile Details of Alumni/Students | SB1/D3/T1 | User Interface For Profile Register
|  | SB1/D3/T2 | Validations for Profile details
|  | SB1/D3/T3 | Connect with the database
|  | SB1/D3/T4 | save the data and upload to the Firebase(Databse)
SB1/US4 | Create/Join the Group | SB1/D4/T1 | User Interface for Create and Join The Group
|  | SB1/D4/T2 | Validations for Group Details
|  | SB1/D4/T3 | Coonnect with the database and save the details
|  | SB1/D4/T4 | Send Group Joining Request from user to server
|  | SB1/D4/T5 | Joining request from server to the Group admin
SB1/US5 |  | SB1/D5/T1
SB1/D5/T2
SB1/D5/T3
SB1/D5/T4
SB1/US27 |  | SB1/D6/T1
SB1/D6/T2
SB1/D6/T3
SB1/D6/T4
SB1/D6/T5
SB1/US27 |  | SB1/D7/T2
SB1/D7/T3
SB1/D7/T4
SB1/D7/T5
SB1/US150 |  | SB1/D8/T1
SB1/D8/T2
SB1/D8/T3
SB1/D8/T4
SB1/US28 |  | SB1/D9/T1
SB1/D9/T2
SB1/D9/T3
SB1/D9/T4
SB1/D9/T5
SB1/US50 |  | SB1/D10/T1
SB1/D10/T2
SB1/D10/T3
SB1/D10/T4
SB1/D10/T5
SB1/US53 |  | SB1/D11/T2
SB1/D11/T3
SB1/D11/T4
SB1/D11/T5
SB1/US55 |  | SB1/D12/T1
SB1/D12/T2
SB1/D12/T3
SB1/D12/T4
SB1/US51 |  | SB1/D13/T1
SB1/D13/T2
SB1/D13/T3
SB1/D13/T4
SB1/D13/T5
SB1/US70 |  | SB1/D14/T1
SB1/D14/T2
SB1/D14/T3
SB1/D14/T4
SB1/D14/T5
SB1/US71 |  | SB1/D15/T2
SB1/D15/T3
SB1/D15/T4
SB1/D15/T5
SB1/US72 |  | SB1/D16/T1
SB1/D16/T2
SB1/D16/T3
SB1/D16/T4

## SB Hours 01
Sprint Backlog 1
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
1 | As a developer I want to develop the hardware so that Wii-mote can be placed on the screen | Search about the hardware setup
Search about components required
Purchase component from Market
Develop the hardware
2 | As a developer I want to search for applications to be developed so that I can identify an application to be developed | Search annotation application
search paint application
search video making application
search audio recording applications
3 | As a developer I want to study about the technology to be used so I can identify the technology for application | Study tutorials
Study tutorials
start with Basics of c#
start with Basics of c#
4 | As a developer I want to begin coding in swings so I can start with designing of the application | start with Basics of c#
start with Basics of c#
|  | coding of onscreen application |  |  |  | 0
|  | coding of onscreen application |  |  |  | 0
5 | As a developer I want to start coding of my application so that I can develop application | coding of onscreen application |  |  |  | 0
|  | coding of onscreen application |  |  |  | 0
Debug the code
Debug the code
6 | As a developer I want to implement my designed application so that I can use it | Implentation of application on virtual screen.
Implentation of application on virtual screen.
Implentation of application on virtual screen.
Implentation of application on virtual screen.
7 | As a developer I will implement the final project in the classrooms so that system can be used by the users at college | Switch on the projector and set the projected screen
Interface it with PC/laptop
Switch on the projector and set the projected screen
Interface it with PC/laptop
8 | As a tester I will check the whole system implemented in classrooms so that final system could be tested | Callibrate WII remote with virtual screen
Use different applications on the virtual screen
Check the changes made at the virtual screen
Checking if it is working effectively with the laptop and not damaged
9 | As a developer I will prepare the final delivarables of the whole system so that I can give the entire system | Prepare all hardware deliverables
Prepare all software deliverables
Prepare a hardware & software guide
Prepare a user manual & guide for the users
10 | As a developer I want to give training to faculty & students so that they can interact with the system & use it | Giving information to users about the project
Project demonstration
Project demonstration
Project to be operated by different users
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch01
Spring Backlog 01 burn down chart
Date | Planned Total Task | Actual Incompleted Task
2018-09-04 | 45 | 40 | Tasks
2018-09-12 | 40 | 40
2018-09-11 | 40 | 35
2018-09-14 | 35 | 35
2018-09-16 | 35 | 35
2018-09-18 | 35 | 35
Days

## SprintBacklog 2
SPRINT BACKLOG 2
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 2 - <Digital College>
| Add Department | SB2/D1/T1 | Designing the GUI | SP
|  | SB2/D1/T2 | Connection with database to fetch the data | RA
|  | SB2/D1/T3 | Testing of the module on localhost and then on server. | RA+SP+PB+RM
| Register TA into the application(using poornima email account) | SB2/D2/T1 | Designing of GUI | PB
|  | SB2/D2/T2 | Validating user input at client level | RM
|  | SB2/D2/T3 | Validating user input at server level | SP
|  | SB2/D2/T4 | Connection with Database to insert the record. | RA
|  | SB2/D2/T5 | Testing of the module on localhost and then on server. | RA+SP+PB+RM
| TA Receiving Confirmation Email | SB2/D3/T1 | Designing of Email(to be send) | PB
|  | SB2/D3/T2 | Send Email via coding using the Mandrill App | SP
|  | SB2/D3/T3 | Connection with database to update the status in the database. | RA
|  | SB2/D3/T4 | Testing of the module on localhost and then on server. | RA+SP+PB+RM
| Register TO into the application(using poornima email account) | SB2/D4/T1 | Designing of GUI | PB
|  | SB2/D4/T2 | Validating user input at client level | RM
|  | SB2/D4/T3 | Validating user input at server level | SP
|  | SB2/D4/T4 | Connection with Database to insert the record. | RA
|  | SB2/D4/T5 | Testing of the module on localhost and then on server. | RA+SP+PB+RM
| TO Receiving Confirmation Email | SB2/D5/T1 | Designing of Email(to be send) | PB
|  | SB2/D5/T2 | Send Email via coding using the Mandrill App | SP
|  | SB2/D5/T3 | Connection with database to update the status in the database. | RA
|  | SB2/D5/T4 | Testing of the module on localhost and then on server. | RA+SP+PB+RM
| Add Subject | SB2/D6/T1 | Designing of GUI | PB
|  | SB2/D6/T2 | Validating user input at client level | RM
|  | SB2/D6/T3 | Validating user input at server level | SP
|  | SB2/D6/T4 | Connection with Database to insert the record. | RA
|  | SB2/D6/T5 | Testing of the module on localhost and then on server. | RA+SP+PB+RM
| Register Timetable Co-ordinator into the application | SB2/D7/T1 | Designing of GUI | PB
|  | SB2/D7/T2 | Validating user input at client level | RM
|  | SB2/D7/T3 | Validating user input at server level | SP
|  | SB2/D7/T4 | Connection with Database to insert the record. | RA
|  | SB2/D7/T5 | Testing of the module on localhost and then on server. | RA+SP+PB+RM
| Timetable Co-ordinator Receiving Confirmation Email | SB2/D8/T1 | Designing of Email(to be send) | PB
|  | SB2/D8/T2 | Send Email via coding using the Mandrill App | SP
|  | SB2/D8/T3 | Connection with database to update the status in the database. | RA
|  | SB2/D8/T4 | Testing of the module on localhost and then on server. | RA+SP+PB+RM

## SB Hours 02
Sprint Backlog 2
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch02
Spring Backlog 02 burn down chart
Date | Planned Total Task | Actual Uncompleted Task
2017-09-25 | 177 | 177 | Tasks
2017-09-28 | 110 | 177
2017-10-02 | 80 | 177
2017-10-05 | 66 | 177
2017-10-07 | 15 | 177
2017-10-09 | 5 | 177
0
Days

## SprintBacklog 3
SPRINT BACKLOG 3
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 3 - <Digital College>

## SB Hours 03
Sprint Backlog 3
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch03
Spring backlog 3 Burnt Down chart
Date | Planned Total Task | Actual Uncompleted Task
2018-10-16 | 120 | 120 | Tasks
2018-10-18 | 110 | 120
2018-10-20 | 80 | 120
2018-10-21 | 25 | 120
2018-10-22 | 15 | 120
2018-10-23 | 0 | 120
0
Days

## SprintBacklog 4
SPRINT BACKLOG 4
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 4 - <Digital College>

## SB Hours 04
Sprint Backlog 4
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch04
Date | Planned Total Task | Actual Uncompleted Task
2019-01-10 | 190 | 190 | Tasks
2019-01-11 | 110 | 190
2019-01-12 | 80 | 190
2019-01-13 | 25 | 190
2019-01-14 | 15 | 190
2019-01-15 | 0 | 190
0
Days